TASKBOARD

| Product Backlog | In Progress | Completed |
| --- | --- | --- |
| - Improve business idea - Customer analysis (WHO) - Value proposition (WHAT) - Marketing channels (WHERE) - Buying behaviour (WHEN) - USP & competitive advantage (WHY) - Feasibility analysis - MVP / Test plan - Documentation updates - Final editing & submission | - Marketing strategy (WHERE, WHEN, WHY) - Feasibility planning - Documentation updates | - Business Case (Deliverable 1) - Survey & research - Initial business idea - Sprint 1 tasks |

WALKTHROUGH

| - What do we need to do to advance this piece of work? | Complete the presentation. Improve slides based on feedback. Refine the business idea. |
| --- | --- |
| - Is anyone working on anything that is not on the board? | No, all team members are working on the presentation and business idea tasks. |
| - What do we need to finish as a team? | Finalize the presentation and make improvements from lecturer feedback. |
| - Are there any bottlenecks or blockers to the flow of work? | Time management, Communication. |

LOGBOOK

| Date: | 13-07-2026 |  |
| --- | --- | --- |
| Monday | - What did I complete since the last standup? | Discussed PC Revival idea. Identified laptop affordability problem. Planned presentation |
|  | - What am I planning to complete between now and the next standup? | Work on slides and problem statement. |
|  | - What are my impediments (or risks or problems)? | Some confusion about what to include. Team not fully aligned. |

| Date: | 14-07-2026 |  |
| --- | --- | --- |
| Tuesday | - What did I complete since the last standup? | Improved business idea. Defined student laptop problem clearly. Helped planned slides |
|  | - What am I planning to complete between now and the next standup? | Work on value proposition and service explanation. |
|  | - What are my impediments (or risks or problems)? | Limited team Collaboration and communication. |

| Date: | 15-07-2026 |  |
| --- | --- | --- |
| Wednesday | - What did I complete since the last standup? | Worked on value proposition. Added ideas for marketing channels (WhatsApp, TikTok, Instagram). |
|  | - What am I planning to complete between now and the next standup? | Finish slides. |
|  | - What are my impediments (or risks or problems)? | Time management. Finalised slides. Practiced presentation. |

| Date: | 16-07-2026 |  |
| --- | --- | --- |
| Thursday | - What did I complete since the last standup? | Presented PC Revival. Got feedback from the lecturer. |
|  | - What am I planning to complete between now and the next standup? | Improve the presentation based on feedback. |
|  | - What are my impediments (or risks or problems)? | Time management and Nervousness during presentations. |

| Date: | 17-07-2026 |  |
| --- | --- | --- |
| Friday | - What did I complete since the last standup? | Worked on improving the presentation using feedback. Reflected on strengths and weaknesses. |
|  | - What am I planning to complete between now and the next standup? | Finalize improvements and prepare for submission. |
|  | - What are my impediments (or risks or problems)? | Some unclear explanations and areas needing improvement. |